## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | Any Portal
1.1 | Search in all published Companies | 5 | Rawan | Abanoub | Antony
2 | External Portal
2.1 | Login for investor | 3 | Mina | Abanoub | Antony
3 | Internal Portal
3.1 | Login for admin, reviewer and lawyer | 3 | Morcos | Abanoub | Antony
4 | Admin
4.1 | As an Admin I should be able to view all details of requests for an account, by either lawyer, reviewer . | 2 | Mina | Abanoub | Antony
4.2 | As an Admin I can search all cases according to a specific field. | 5 | Antony | Maria | Morcos
5 | Investor
5.1 | As an Investor I should be able to pay fees online if the reviewer approved. | 8 | Abanoub | Rawan | Antony
5.2 | As an investor , I should be notified with the amount and the due date (fees calculation) | 2 | Aya | Antony | Maria
5.3 | As an investor , I should be able to view rejected apps and update them | 2 | Aya | Antony | Maria
6 | Lawyer
6.1 | As a Lawyer , I Can view all my pending cases (needs lawyer review) | 2 | Yomna | Abanoub | Morcos
6.2 | As a Lawyer , I Can view all my Finalized cases . (after lawyer accepted) | 2 | Aya | Abanoub | Antony
6.3 | As a Lawyer , I can view which lawyer is working on specific case | 2 | Yomna | Abanoub | Antony
6.4 | As a Lawyer , I should be able to view a case if there is not any other lawyer working on.(Workpage) | 2 | Rafeek | Abanoub | Antony
6.5 | I can search for an application by specific field | 5 | Rafeek | Abanoub | Antony
6.6 | Assign me to this case | 3 | Yomna | Abanoub | Antony
6.7 | Fees calculation after accepting, and check if rejected and updated by lawyer | 5 | Dalia | Abanoub | Antony
6.8 | Only if a lawyer initated the case he can update it | 2 | Dalia | Abanoub | Antony
7 | Reviewer
7.1 | As a Reviewer i can search for a specific detail in all the applications. | 5 | Maria | Abanoub | Antony
7.2 | Assign me to this case | 3 | Morcos | Abanoub | Antony
8 | Unit Tests
8.1 | Anyone assigned to stories in sprint 1,2 &3 ,do it's unit tests
zz