## Sheet1
Unique ID | User story | Crud | Story Points | Assignee | Depends on | Testing User Story?
1 | Investor
1.1 | I can edit my account’s secondary details in the external portal and get notified if any required fields are missing/incorrect. | Update | 8 | antony | 1.2 | rawan
1.2 | I should be sign up for an account as an investor and get notified if any required fields are missing/incorrect. | Create | 3 | rawan
1.3 | sign in to my account in the external(investor) portal as an investor and get notified if any required fields are missing/incorrect. | Read | 2 | antony | 1.2 | rawan
1.4 | As an admin i can decativate an Investor account | Delete | 5 | maria | 1.2 | rawan
2 | Admin
2.1 | As an admin can deactivate an admin's account | Delete | 5 | mina | 2.2 | maria
2.2 | I can sign up for an account and get notified if any required fields are missing/incorrect. | Create | 3 | maria
2.3 | I can sign in to my account in the external portal and get notified if any required fields are missing/incorrect. | Read | 2 | mina | 2.2 | maria
2.4 | I can edit my account's secondary details in the internal portal and get notified if any required fields are missing/incorrect | Update | 8 | maria | 2.2 | maria
3 | Lawyer
3.1 | As an admin I can delete a lawyer's account | Delete | 5 | morcos | 3.2 | morcos
3.2 | I should sign up for an account to be approved by the admin and get notified if any required fields are missing/incorrect. | Create | 3 | morcos
3.3 | I can edit my account’s secondary details and get notified if any required fields are missing/incorrect. | Update | 8 | rawan | 3.2 | morcos
3.4 | I can sign in to my account in the internal portal and get notified if any required fields are missing/incorrect. | Read | 2 | rawan | 3.2 | morcos
4 | Reviewer
4.1 | I can edit my account’s secondary details and get notified if any required fields are missing/incorrect. | Update | 8 | rafeek | 4.3 | rafeek
4.2 | As an admin i can delete reviewer's account | Delete | 5 | aya | 4.3 | rafeek
4.3 | I should sign up for an account to be approved by the admin and get notified if any required fields are missing/incorrect. | Create | 3 | rafeek
4.4 | I can sign in to my account in the internal portal and get notified if any required fields are missing/incorrect. | Read | 2 | aya | 4.3 | rafeek
5 | Form
5.1 | As an investor , I Can fill Company Establishment form and get notified if any required fields are missing/incorrect . | Create | 3 | youmna
5.2 | As an Investor ,I Can update my form | Update | 8 | dalia | 5.1 | youmna
5.3 | As an Investor ,I Can delete my form | Delete | 5 | youmna | 5.1 | youmna
5.4 | As an Investor ,I Can Read my form | Read | 2 | dalia | 5.1 | youmna
6 | Lawyer_form
6.1 | As a lawyer, I Can fill lawyer_form and get notified if any required fields are missing/incorrect . | Create | 3 | dalia
6.2 | As a lawyer, I Can update the form | Update | 8 | abanoub | 6.1;5.1 | dalia ; youmna
6.3 | As a lawyer,Investor ,reviewer I should be able to view the lawyer's form . | Read | 2 | youmna | 6.1;5.1 | dalia ; youmna
7 | Reviewer_form
7.1 | As a Reviewer, I Can fill a Reviewer_form to approve or reject with comment and get notified if any required fields are missing/incorrect . | Create | 3 | abanoub
7.2 | As a Reviewer ,I Can update the form. | Update | 8 | aya | 7.1;6.1 | dalia ; abanoub
7.3 | As a investor, I should be able to view my reviewer form. | Read | 2 | rafeek | 7.1;6.1 | dalia ; abanoub
8 | Company
8.1 | As an admin ,I can delete a company | Delete | 5 | antony | 7.1;8.3 | mina ; abanoub
8.2 | As an admin, I can view all companies in the system with their details. | Read | 2 | morcos | 7.1;8.3 | mina ; abanoub
8.3 | As an investor , a company must be created when i pay my fees for the approved form. | Create | 3 | mina