## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2 | Estimate Report | VS1 | VS2 | VS4 | VS4 * I | I=VS2/VS1
1 | External Portal
1.1 | As an external user, I should be able to view all published companies | 2 | Dalia | Abanoub | Rawan |  | 126 Stories/70=1.8 | 61 Stories/35=1.7 | 32 Story Points/15=2.13 | 0.94*2.13=2.01 | 1.7/1.8=0.94
1.2 | As a user, I should be able to update my profile | 5 | Maria | Maria | Mina
2 | Internal Portal
2.2 | As an admin I should get all pending users and approve/reject and add comments on each form | 3 | Morcos | Antony | Mina
2.3 | As an inernal portal user, i should be able to search for a specific case | 5 | Mina | Morcos | Maria
3 | Lawyer
3.1 | As a lawyer, I should get all my forms and approve/reject and add comments on each form | 5 | Rafiq | Dalia | Rafiq
3.2 | As a lawyer, I should get all my finalized cases | 3 | Dalia | Aya | Youmna
3.3 | As a lawyer, I should be able to fill a form | 5 | Mina | Youmna | Rafiq
3.4 | As a lawyer, I should be able to update form that I created | 5 | Aya | Mina | Antony
3.5 | As a lawyer, I can be assigned to a form | 5 | Morcos | Rawan | Maria
3.6 | As a lawyer, I should be able to calculate fees | 5 | Abanoub | Dalia | Youmna
4 | Admin
4.2 | as an admin, I should view all lawyers | 2 | Rawan | Maria | Aya
4.3 | as an admin, I should view all investors | 2 | Youmna | Rafiq | Maria
4.4 | as an admin, I should view all reviewers | 2 | Aya | Rafiq | Maria
4.5 | As an admin , I should get all users and approve/reject and add comments on each form | 5 | Morcos | Beno | Rafiq
4.6 | As an admin, I should see forms of a lawyer(inside a lawyer profile) | 3 | Youmna | Aya | Morcos
4.7 | As an admin, I should be able to get a specific user | 3 | Maria | Rafiq | Mina
5 | Reviewer
5.1 | As a reviewer, I should get all my forms and approve/reject and add comments on each form | 3 | Aya | Morcos | Aya
5.3 | As a reviewer, I can be assigned to a form | 3 | Maria | Abanoub | Rafiq
6 | Investor
6.1 | As an investor, I should be able to update a form | 5 | Rawan | Abanoub | Morcos