## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | as a admin,investor,user or lawyer , I should be able to log in | 3 | Morcos | Abanoub | Antony
1.1 | as a lawyer or reviewer I shoud be able to view my working forms | 2 | Mina | Abanoub | Rafiq
1.2 | As an admin I should be able to view all entity employees | 2 | Abanoub | Rafiq | Antony
1.3 | as a reviewer, or lawyer I should be able to see my accepted and rejected cases | 3 | Antony | Abanoub | Rafiq
1.4 | As an Admin I can search all cases according to a specific field. | 5 | Rafiq | Abanoub | Antony
1.5 | As a user, I should be able to view form requirements | 3 | Rawan | Antony | Morcos
1.6 | as an investor I should be able to view my pending/running companies | 3 | Dalia | Antony | Rafiq
1.7 | as a user I should be able to sign up(Create an account) | 5 | Youmna | Abanoub | Rafiq
1.8 | As an investor , I should be able to view rejected apps and update them | 3 | Aya | Rafiq | Antony
1.9 | As a Lawyer , I can view which lawyer or reviewer is working on specific case | 3 | Maria | Antony | Abanoub